## Details
Stakeholder Analysis Worksheet
Project Name: | Super Widget 2.0
Support | Department | Role | Summary of Interests (Expectations) | Summary of Impact (How They're Affected) | Power (Level of Authority) | Interest (Level of Involvement) | Overall Importance to the Project | Strategy for Managing | Next Steps
Joyce Williams | I.T | Sponsor |  |  | 8 | 5 | 9
Bob Johnson | I.T. | Director |  |  | 6 | 8 | 7
Bill Smith | Marketing | Supervisor |  |  | 3 | 6 | 3
John Koehler | Marketing | Supervisor |  |  | 4 | 1 | 9
Against | Department | Role | Summary of Interests (Expectations) | Summary of Impact (How They're Affected) | Power (Level of Authority) | Interest (Level of Involvement) | Overall Importance to the Project | Strategy for Managing | Next Steps
Bob Crachett | Marketing | VP/Sponsor on the Marketing side. | He wants minimal impact on his team. In addition, he's all about the date. | Will require many of his people throughout the project. Generally concerned that we won't hit the date which would cause problems with his customers. | 9 | 6 | 2 | Keep him in the loop. Work on developing the relationship. Lunch with him once a month. | Schedule the next lunch.
Ed Bates |  |  |  |  | 5 | 2 | 5
Frank Stein | Compliance | Director. Process compliance | Focused on making sure we follow the new process changes. | His success depends on us using the process and the project being successful. He thinks we're not a good case study for the process, that we'll fail. | 8 | 9 | 7 | Keep him in the loop. Work on developing the relationship.
Neutral | Department | Role | Summary of Interests (Expectations) | Summary of Impact (How They're Affected) | Power (Level of Authority) | Interest (Level of Involvement) | Overall Importance to the Project | Strategy for Managing | Next Steps
Jill Lewis |  |  |  |  | 4 | 8 | 2
Sara Barrett |  |  |  |  | 9 | 2 | 2
Zachary Cooney |  |  |  |  | 3 | 9 | 2

## Stakeholder Analysis Chart
Super Widget 2.0